## Trustees Meeting Tracker
Tregonwell Almshouse Trust: Trustee Meeting Action Tracker
Item # | Action | Responsible | Target Date | Comments
1 | Clerk to put agendas and minutes on the web site. | Mark Castle-Smith | 2024-12-01 | 30/10/2024: Draft web site in progress and due to go live following 6 Nov Trustees meeting for approval.
2 | Clerk to produce action tracker to be located on our web site. | Mark Castle-Smith | 2024-12-01 | 30/10/2024: Tracker completed, to go on web site when go live.
3 | Update, reformat and place Resident's Handbook on the Trust's web site. | Mark Castle-Smith | 2025-02-28 | Ensure letter of appointment is updated to match provisions in the Resident's Handbook
4 | Put in place Quniquennial review due in 2025. | Mark Castle-Smith | 2025-08-01 | 30/10/2024: Rate for review agreed and estimate of costs gathered from architect and reflected in 2025 budget forecast. Aim to book in review for early March 2025 to allow full summer period for recommended external works.
5 | Prepare budget forecast for November meeting. | Mark Castle-Smith | 2024-11-06 | 30/10/2024: End of year cash and investment forecast, 2025 budget completed and ready to present to Trustees at 6 Nov meeting for approval.
6 | Investigate our current investment portfolio and make recommendations for any changes. | Rodger Pressland | 2025-03-01 | 30/10/2024: Following calls to M&G, to confirm two letters are shortly expected with details of dates that our portfolio started and how folio returns are calculated. The annual return seen this year is reflected within the 2024 end of year forecast spreadsheet.
7 | Fire and Legionnaires risk assessments to be completed. | Mark Castle-Smith | 2025-03-01 | 30/10/2024: Clerk getting a range of prices and will be contracting shortly. Aim is to be completed prior to quinquennial review.
8 | Fund raising event of Moveable Feast to be organised. | Susie Castle-Smith | 2025-03-30 | 30/10/2024: Organisers have agreed date for event in principle. Waiting to confirm availability of Reading Rooms and Church prior to advertising for this event.
9 | Clerk to ask Dawn if she would like to lead on organising a coffee morning in the Reading Rooms to help raise funds and awareness of the Almshouse Trust. | Dawn Wyatt | 2025-06-01 | 30/10/2024: Mark and Dawn have had an initial discussion regarding this event.
10 | Clerk to implement a Trust web site. | Mark Castle-Smith | 2024-12-01 | 30/10/2024: Draft web site created for approval at 6 Nov 24 meeting after which the site can go live. Trustees to discuss contents and what should be kept in the private area of the web site.
11 | Clerk to email all Trustees ref review of the Trust's Scheme for discussion at 6 Nov 24 meeting. | Mark Castle-Smith | 2024-11-06 | 30/10/2024: Clerk emailed all Trustees for comment prior to meeting so he can present ideas to the Chair prior to the meeting.
12 | Clerk to organise decommissioning of the current alarm system. | Mark Castle-Smith | 2025-03-01
13 | Clerk to write policies and procedures for Trustees approval in line with legal and Almshouse Association recommendations. | Mark Castle-Smith | 2024-12-31 | 30/10/2024: Draft Financial/Investment policy completed for Trustees approval at 6 Nov meeting. If format approved all other polies will be drafted by end of the year.
14 | All Trustees to register with the Almshouse Association web site so that they can access governance information as well as monitor potentially useful courses etc. | All Trustees | 2024-11-06 | 30/10/2024: Trustees to report progress at 6 Nov meeting.
15 | Clerk to set up Trust What's App Group. | Mark Castle-Smith | 2024-11-06 | 30/10/2024: Invitations sent out to all Trustees and Residents. NB: One Resident does not have mobile phone access.
16 | Complete de-registration as a social housing provider. | David Duncombe-Anderson | 2024-12-31 | 30/10/2024: David to provide update at 6 Nov 24 meeting.
17 | Put in place programme of work to meet recommendations from the Almshouse Association Health Check. | Mark Castle-Smith | 2024-12-31

## Clerk Action Tracker
Tregonwell Almshouse Trust: Clerk Action Tracker
Item # | Action | Responsible | Target Date | Status | Comments
1 | Contract for Fire Risk Assessment | MCS | 2025-02-01 | Completed | Fire Risk Assessement completed and on file
2 | Contract for Legionairres Risk Assessment | MCS | 2025-02-01 | Completed | Risk Assessement completed and on file
3 | Complete Web Site and go live | MCS | 2024-12-01 | In Progress
4 | Create buldings maintenance book/records | MCS | 2025-02-01 | Completed
5 | Complete all policies and procedures | MCS | 2024-12-31 | In Progress
6 | Create master list of when all mandatory actions need to be completed and when next due | MCS | 2025-02-01 | Not Yet Started
7 | Add resident's to What's App Group | MCS | 2024-12-01 | Not Yet Started
8 | Create Monthly check sheet | MCS | 2025-02-01 | Not Yet Started
9 | Create list of maintenance tasks to be completed (within building maintenance records) | MCS | 2025-02-01 | Not Yet Started
10 | Spare keys in key safes around building | MCS | 2025-01-01 | In Progress | Key safes have been bought and locations identified
11 | Investigate grants for solar panels, heat pumps etc | MCS | 2025-12-01 | In Progress | Research started
12 | Thermal loss calculations and IR vs modern storage heaters | MCS | 2025-08-01 | Not Yet Started
13 | Go through 2020 Quinquennial reviews and pre questionnaire letter, to pick up relevant actions and prep for 2025 review | MCS | 2025-01-01 | Completed | Tracker completed and created blank 2025 tracker
14 | Produce monthly diary (from DDA template) and add to this spreadsheet | MCS | 2024-12-01 | Not Yet Started
15 | Check liquidity of our M&G Investments | MCS | 2024-11-03 | Completed | Info DDA and determined that the multi asset fund is completely liquid and can withdraw funds at any time.
16 | Investigate Smartwater for roof lead | MCS | 2025-05-01 | In Progress | Get advice during quinquennial review
17 | Rewrite and get signed Residents letter of appointment | MCS | 2025-03-01 | Not Yet Started | In conjunction with rewrite of resident's handbook
18 | Produce and get updated signed NOK forms | MCS | 2025-04-01 | Not Yet Started
19 | Go through Almshouse Association templated documents for implementation as relevant | MCS | 2025-05-01 | Not Yet Started
20 | Contract for an EPC | MCS | 2024-10-30 | Completed | EPC on Government web site and rated at Cat E
21 | Check EICR for next inpspection | MCS | 2024-11-30 | Completed | Inspection booked for Mar 25
22 | Download 'Decent Homes Standard' and cross reference complioance | MCS | 2025-06-01 | Not Yet Started | As we are not a registered provider we do not need to meet this provisions but the Almshouse Association recommend that it is good practice to align with the intent of these requirements (from the Regulalator for Social Housing).
23 | Investigate modern systems to reduce electricity bills for resident's and potentially decrease our carbon footprint | MCS | 2025-11-01 | In Progress | What heating ssytemshould we be using (IR, modern Lot compliant 20 storage heaters, central heating with air source heat pump, air to air heat pump etc), potential for battery storage and solar panels.
24 | Think about the Almshouse application form, how do make it easily available online as well as a version that can be completed easily without access to a computer and to keep it as simple and as accessible as possible. | MCS | 2025-08-01 | Not Yet Started
25 | Rewrite and update the Resident's Handbook | MCS | 2025-01-30 | In Progress | Align with the Letter of Appointment
| Ctreate Fire Risk Assessment action plan | MCS | 2025-03-30 | Not Yet Started
| Create Legionella Risk Assessment action plan | MCS | 2025-03-30 | Not Yet Started

## Calendar
Almshouse Drumbeat Calendar
Date | Action
Mid January | Reconcile bank statements and Income /expenditure from the following year
End January | Produce accounts ready for auditor
February | Send accounts to auditor
March | Agenda for Trustees Meeting March meeting to incude electction of Chairman and adopt/sign the accounts Annual return to the Charity Commission Annual return to the Housing Ombudsman Signed accounts (pdf) submission to the HCA to public.register@hca.qsi.gov.uk
April | Statistical Data Return (SDR) fror the Regulator of Social Housing by end May
May
June | Agenda for June Meeting
July
August
September | Renew TV concessions as appropriate
October | Agenda for next Trustees Meeting Prepare cash flow for year end Prepare budget for following year
November | November meetinhg to incude meeting dates for next year Budget including maintenance contributions for next year Financial end forecast Notgify residents of new maintenance contribution changes
December | Invoice for Reading Room rent and insurance Residents christmas presents Invoice Clerk's expenses
NB | Monthly bank reconciliation
Fire equipment checks
Policy reviews
Legionella checks
Fire practices
Cooker hood inspections
Emergency lighting checks
Ventaxi servicing
Hot water systems servicing

## 2020 QR Tracker
Tregonwell Almshouse Trust: 2020 Quinquennial Review Tracker
Report Dated 26 August 2020
Report # | Description | Report Description # | Estimated cost (ex VAT) | Actual Cost (inc) | Action | RAG Status | Date Completed | Comments
A | Urgent , Requiring Immediate Attention
1 | Replace broken / slipped tiles and slates | 7a,b,c,d,e,j,k,l,m,p,q,r,s,t | 700 | NK | Tiles from Kavanagh, Colin Joyce to action | Completed | 2021-07-19
2 | Clear rainwater goods | 8a,f,g | 60 | NK | Ian Rogers and Colin Joyce | Completed | Ongoing
3 | Ease door | 15Cd | 20 | NK | David DA | Completed | 2022-07-13
4 | Investigate and remedy dampness | 16Cb,Db | 500 | 2265.74 | Washing machine | Completed | 2021-03-11 | Washing machine faulty repair
|  | Total Costs | 1280 | 2265.74
B | Requires Attention within 12 Months
1 | Repair chimney | 2a,10a,b,c,g,14b | 2000 | 6880 | Colin Joyce to action in 2021 | Completed | 2021-07-19
2 | Remove vegetation from walls and point in open gaps | 7u,11m,t,y,20Aa,b,c,21i,t | 500 | NK | Ian Rogers, Martin Foers to action | Completed | 2021-08-16
3 | Redecorate gutters and repair brackets | 8b,c,e,15Fb | 1500 | NK | Neil Joyce / Colin Joyce? | Not Yet Started |  | For action in 2025
4 | Redecorate seating | 11b | 50 | NK | Neil Joyce to action | Completed | 2021-03-30
5 | Improve arrangement of rainwater goods | 11u | 150 | NK | Colin Joyce to action | Completed | 2022-02-28
6 | Re-secure cables | 11v | 20 | NK | David DA to action | Completed | 2021-10-15
7 | Re-distribute insulation | 14c | 30 | NK | Jonny Moss to action | Completed | 2022-01-13
8 | Re-shape / replace squashed ducts | 14e | 150 | NK | Jonny Moss to action | Completed | 2022-01-13
9 | Repair / rebond vinyl | 15Gc,16Gc,17Fd | 150 | NK | Wessex carpets to action | Completed | 2021-11-02
10 | Repair corner of step | 19Aj | 50 | NK | Wessex carpets to action during flooring | Completed | 2021-04-26
11 | Touch up decorations | 19Eg,Fe,Ga | 100 | NK | Neil Joyce to action | Completed | 2021-03-30
12 | Repair handrail | 21n | 60 | NK | David DA to investigatre | Completed | 2021-10-15
|  | Total Costs | 4760 | 6880
C | Requires Attention within the Quinquennial Period
1 | Point in corbel | 11c | 30 | NK | Colin Joyce to action | Completed | 2022-05-22 | Lime mortar slate grey
2 | Remove loose pointing and repoint if required | 11d | 500 | NK | Colin Joyce to action | Completed | 2022-05-22 | Lime mortar slate grey
3 | Replace spalled brick | 11l | 80 | NK | Colin Joyce to action | Completed | 2022-10-12
4 | Repair and redecorate external joinery | 12b,e,g,h,j,13a,15Ea,17Ad,18Ae,19Lb,20Af | 900 | NK | Colin Joyce to action carpentry Neil Joyce to action decoration | Completed | 16/05/2023 20/5/22
5 | Redecorate rusting ironwork in roof voids | 14f | 500 | NK |  | Not Yet Started |  | For action in 2025
6 | Ease / adjust doors and windows | 15Ae,Fc,16Df,18Fd,Ge,19Cd,20Bf | 60 | NK |  | Not Yet Started |  | For action in 2025
7 | Redecorate window | 15De | 50 | NK | Neil Joyce to action | Completed | 2022-07-13
8 | Repair wall by socket | 15Fd | 30 | NK | Neil Joyce to action | Completed | 2022-07-13
9 | Repair and redecorate kitchen ceiling | 19Ca | 100 | NK | Neil Joyce to action | Completed | 2021-03-30
10 | Repair plaster and redecorate | 19Jf | 500 | NK |  | Not Yet Started |  | For action in 2025
11 | Repair cracks | 21d | 100 | NK | Colin Joyce to action | Completed | 2022-10-01
|  | Total Costs | 2850 | 0
D | Items Requiring Attention beyond the Quniquennial Period
1 | Repair copings | 10e,f | 500 | NK |  | Not Yet Started
2 | Repair quoin | 11a | 200 | NK |  | Not Yet Started
|  | Total Costs | 700 | 0
E | A Desirable Improvement with No Timescale
1 | Replace downpipe | 11o | 100 | NK | Not considered necessary. | No Action | NA | The roof area covered is small and as long as the drain, not a gully, is kept clear there is no need. A nicety not detrimental.
2 | Point in gap by doorframes | 11p | 60 | NK | Missed, not yet done | Not Yet Started | NA | To be completed 2025
3 | Replace vinyl | 16Dc | 500 | NK | Vinyl replaced | Completed | 2021-03-01
4 | Add safety film to glazing in doors | 16Ed | 100 | NK | Not sure this is required. Decided no action | No Action | NA | There were three identical doors installed during Project 2007 (Side / Back door to Nos 1, 2 and the joint one for Nos 3 & 4). This potential issue had not been raised by the previous two surveys & I could not check with the builder who had gone bust, some 2 years after Project 7's completion; so I made a judgement that the correct glass was actually in place.
5 | Improve ventilation | 16Ga,17Fe | 200 | NK | Vent Axia units installed. | Completed | NK | No 2 = there were two issues on the corner staining to the ceiling - there had been water ingress from the gully above not assisted by the air circulation system not operating correctly, both issues were corrected by repair to the main roof lead flashing (it took two goes to resolve where the leak was coming from) and the upgrading of the Vent-Axia unit, followed by re-plastering and re-decoration. No 3 = there is no doubt that this area was & possibly still is potentially damp, one solution, well aide, was to replace the down pipe outside by doubling the diameter of the down pipe itself with a larger hopper (the roof area covered by this down pipe was overloading the original pipe with a smaller hopper, so water was regularly cascading down the wall); in addition, and I have mentioned this to the Residents, "please do not leave the window open as the air circulation system cannot extract effectively"! Redecoration has taken place and to date I am not aware that the issue continues. This back area is North facing, sun rarely if ever penetrates, leading to a permanent cool damp atmosphere.
6 | Redecorate ceiling | 17Ba | 250 | NK | Redecoration has been done. | Completed | NK | It should be noted that the Vent-Axia system does lead to some condensation leakage from time to time, significant changes in temperature the prime cause; having said that, the introduction of these systems has been a dramatic success
7 | Redecoration to areas affected by damp | 17Da,Fa,b,18Da,19Da,Fa,Ha | 600 | NK | Redecoration c ompleted with exception of No.4 (See comments). | Completed | NK | No 3 kitchen - the repointing, with lime mortar, of the chimneys has certainly helped; however, during the quinquennial period there was again a failure, requiring a replacement Vent-Axia unit, redecoration of the kitchen has been therefore done twice! Bathroom see 5 above. No 4 kitchen - decoration of No 4 is not really possible, I am afraid I just noted the problem, it does not appear to be significant - next! RR decorations done, one area at least needs redoing.
8 | Improve security of windows | 19Al | 50 | NK | Reading Room. | Not Yet Started | NA | This needs a specialist to resolve, over the years the west window has flexed and no longer perfectly aligns. Research to find an expert with a solution is ongoing. Hirers have been advised not to open this window unless really necessary, with care and limited force it remains secure.
9 | Upgrade glazing | 19Cf | 200 | NK | Not considered necessary. | No Action | NA | Not considered a requirement.
10 | Replace bolt to WC door | 19Ei | 50 | NK | Not considered necessary. | No Action | NA | As is demonstrated by the need or not for cleaning the gents loo as it is not overly used, the latch offers privacy to the toilet cubicle, more use is made of the urinals.
11 | Repair fence | 21k | 500 | NK | Not considered necessary. | No Action | NA | There do seem to me more important things to worry about and there is no security implication, it needs to be looked at in the round!
12 | Redecorate sheds etc | 21p,s | 150 | NK | Treated with Cuprinol and roofs reopaired. | Completed | 2022-06-01
13 | Add contrasting nosings | 21r | 60 | NK | Not considered necessary. | No Action | NA | The cutting back of any vegetation overspill was routinely conducted when the hedges were usually done in June and again when tree pruning and fallen leaf clearing in late autumn. A nicety not detrimental, and with sensible hand rails there are considered no real safety concerns.
|  | Total Costs | 2820 | 0
M | Routine Maintenance which can be done without professional advice or listing building consent
1 | Apply Smartwater | 7v | Self Help? | NK | David DA | No Action | NA | Deemed too expensive for additional security. Almshouses are always occupied by most of the residents.
2 | Clear rainwater goods at least twice per year | 8a,g | 150 | NK | Ian Rogers | Completed | Ongoing
3 | Periodically check drains | 9c | Self Help? | NK | Ian Rogers | Completed | Ongoing
4 | Monitor cracks | 11s | Self Help? | NK | David DA | Completed | Ongoing
5 | Replace screws | 12i | Self Help? | NK | Colin Joyce | Completed | 2022-05-01
6 | Adjust cupboard door | 16De | Self Help? | NK | David DA | Completed | 2022-07-01
7 | Replace missing screw | 17Ad | Self Help? | NK | Colin Joyce | Completed | 2022-10-01
8 | Tighten handles | 17Fd | Self Help? | NK | David DA | Completed | 2022-07-01
9 | Replace missing chair feet | 19Ai,Je | 20 | NK | NK | Completed | 2021-08-01
10 | Unwrap' kitchen cupboards | 19Ce | Self Help? | NK | David DA | Completed | 2022-10-01
11 | Cleaning | 19Eb,f | Self Help? | NK | David DA | Completed | 2021-08-01
12 | Relocate ramps | 19Fd | Self Help? | NK | NK | Completed | 2021-08-01 | Now in Rear Storeroom
13 | Replace light pull | 19Ge | Self Help? | NK | Colin Joyce | Completed | 2022-10-01
14 | Replace missing bolt | 19Hf | Self Help? | NK | Colin Joyce | Completed | 2022-10-01
15 | Replace catch | 19Jc | Self Help? | NK | Colin Joyce | Completed | 2022-10-01
16 | Decorate benches | 21c | Self Help? | NK | David DA/Neil Joyce | Completed | Ongoing
17 | Gardening | 21g,r | Self Help? | NK | Ian Rogers | Completed | 2022-10-01
18 | Periodic inspection and pruning of trees | 21l,m | 250 | NK | David DA | Completed | NK
19 | Dispose of cable | 21q | Self Help? | NK | No Action | No Action | NA | Decision to ignore at this stage
20 | Routine testing and servicing of building services | 22 | 500 | NK |  | Completed | Ongoing
|  | Total Costs | 920 | 0

## 2025 QR Tracker
Tregonwell Almshouse Trust: 2025 Quinquennial Review Tracker
Report Dated XX 2025
Report # | Description | Report Description # | Estimated cost (ex VAT) | Actual Cost (inc) | Action | RAG Status | Date Completed | Comments
A | Urgent , Requiring Immediate Attention
1 | Stuff TEST |  |  |  |  | Not Yet Started
2 | [5 empty] | Not Yet Started
3 | [5 empty] | Not Yet Started
4 | [5 empty] | Not Yet Started
|  | Total Costs | 0 | 0
B | Requires Attention within 12 Months
1 | [5 empty] | Not Yet Started
2 | [5 empty] | Not Yet Started
3 | [5 empty] | Not Yet Started
4 | [5 empty] | Not Yet Started
5 | [5 empty] | Not Yet Started
6 | [5 empty] | Not Yet Started
7 | [5 empty] | Not Yet Started
8 | [5 empty] | Not Yet Started
9 | [5 empty] | Not Yet Started
10 | [5 empty] | Not Yet Started
11 | [5 empty] | Not Yet Started
12 | [5 empty] | Not Yet Started
|  | Total Costs | 0 | 0
C | Requires Attention within the Quinquennial Period
1 | [5 empty] | Not Yet Started
2 | [5 empty] | Not Yet Started
3 | [5 empty] | Not Yet Started
4 | [5 empty] | Not Yet Started
5 | [5 empty] | Not Yet Started
6 | [5 empty] | Not Yet Started
7 | [5 empty] | Not Yet Started
8 | [5 empty] | Not Yet Started
9 | [5 empty] | Not Yet Started
10 | [5 empty] | Not Yet Started
11 | [5 empty] | Not Yet Started
|  | Total Costs | 0 | 0
D | Items Requiring Attention beyond the Quniquennial Period
1 | [5 empty] | Not Yet Started
2 | [5 empty] | Not Yet Started
|  | Total Costs | 0 | 0
E | A Desirable Improvement with No Timescale
1 | [5 empty] | Not Yet Started
2 | [5 empty] | Not Yet Started
3 | [5 empty] | Not Yet Started
4 | [5 empty] | Not Yet Started
5 | [5 empty] | Not Yet Started
6 | [5 empty] | Not Yet Started
7 | [5 empty] | Not Yet Started
8 | [5 empty] | Not Yet Started
9 | [5 empty] | Not Yet Started
10 | [5 empty] | Not Yet Started
11 | [5 empty] | Not Yet Started
12 | [5 empty] | Not Yet Started
13 | [5 empty] | Not Yet Started
|  | Total Costs | 0 | 0
M | Routine Maintenance which can be done without professional advice or listing building consent
1 | [5 empty] | Not Yet Started
2 | [5 empty] | Not Yet Started
3 | [5 empty] | Not Yet Started
4 | [5 empty] | Not Yet Started
5 | [5 empty] | Not Yet Started
6 | [5 empty] | Not Yet Started
7 | [5 empty] | Not Yet Started
8 | [5 empty] | Not Yet Started
9 | [5 empty] | Not Yet Started
10 | [5 empty] | Not Yet Started
11 | [5 empty] | Not Yet Started
12 | [5 empty] | Not Yet Started
13 | [5 empty] | Not Yet Started
14 | [5 empty] | Not Yet Started
15 | [5 empty] | Not Yet Started
16 | [5 empty] | Not Yet Started
17 | [5 empty] | Not Yet Started
18 | [5 empty] | Not Yet Started
19 | [5 empty] | Not Yet Started
20 | [5 empty] | Not Yet Started
|  | Total Costs | 0 | 0

## Residents & Trustees
Residents and Trustees Details
Residents
Almshouse | Resident | DoB | Occupancy | Tel No | email | NoK Name | NoK Address | NoK Relationship | Nok Tel No | NoK email
No 1 | Ann Fookes | 1940-06-10 | 2022-09-01 | 01258 881269 | annfookes@hotmail.com | Alexander Cobbett | 52 Whitefield, West Morden, BH20 7DU | Son | 01929 459735
No 2 | Brian Lawrence | 1936-07-30 | 2024-02-01 | 07510 878989 | brianolive3@gmail.com | Sharon Lawrence | 21 Milton Abbas, Blandford Forum, DT11 0BL | Daughter | 07917 627100 | sharonlawrence13@gmail.com
No 3 | Paul & Anthea Battrick | 11/5/58 2/8/40 | 2016-06-01 | 01258 269348 | pabattrick@aol.com | ken Battrick | 7 Milton Abbas, Blandford Forum, DT11 | Father | 01258 880748
No 4 | Martin Foers | 1940-02-14 | 2009-06-29 | 01258 881594 07810 437843 | mfoers@tiscali.com | Melissa Hutchins | 8AHill Hook Rd, Four Oaks, Sutton Coldfield, B74 4EF | Daughter | 07718 207377
Trustees
Role | Name | Date Appt'ed | Re-election | Tel No | email | DoB | Address
Chair | Rodger Pressland | 2022 | 2026-03-09 | 07894 513004 | rodgerpressland@gmail.com | 1959-04-04 | 33 Milton Abbas, DT11 0BL
Ex Officio | Rev Lewis Pearson | 2013 | NA | 01258 880482 | revlewispearson@gmail.com | 1982-07-09 | The Rectory, Winterborne Stickland, DT11 0NL
PCC Rep | David Duncombe-Anderson | 2023 | 2027-02-20 | 01258 880481 | davidda2021@gmail.com | 1944-08-07 | Brookside, Milton Abbas, DT11 0BQ
Co-opted | Dawn Wyatt | 2023 | 2027-06-20 | 01258 880035 | digger.dawn@hotmail.com | 1963-05-07 | Hill Lodge, Milton Abbas, DT11 0AZ
Co-opted | Susie Castle-Smith | 2019 | 2027-03-25 | 07971 886290 | susiecs@btinternet.com | 1964-05-09 | 42-43 Milton Abbas, DT11 oBP

## No1 Maintenance
No 1 Tregonwell Almshouse Maintenance Record
Date | Maintenance Action | Company | Labour Cost | Materials Cost | Comments
2024-01-24 | Replaced shower thermostic mixer | David Kimber | 100 |  | Deteriorated due to excessive limescale

## No 2 Maintenance
No 2 Tregonwell Almshouse Maintenance Record
Date | Maintenance Action | Company | Labour Cost | Materials Cost | Comments
2024-12-05 | Replace front door light | Milton Abbas Handyman | 15 |  | Screwfix
2025-01-14 | Economy 7 Hot water not working. Investigated and cleaned contacts on hot water tank thermostat. | Milton Abbas Handyman | 25

## No 3 Maintenance
No 3 Tregonwell Almshouse Maintenance Record
Date | Maintenance Action | Company | Labour Cost | Materials Cost | Items Installed/Painted etc | Comments
2025-01-04 | Replace kitchen and hall fire alarms as they were constantly raising false alarms. | Milton Abbas Handyman | 20 |  | Aico Ei146 Optical Smoke Alarm (Expiry 08/35) Aico Heat Alarm Ei144e (Expiry 01/35) | Sourced from Screwfix
2024-01-24 | Replaced shower thermostic mixer | David Kimber | 150 |  | Deteriorated due to excessive limescale
2025-01-24 | Cleared drains | Canford Drains | 156 | 0 | Shower drain backing up. Drain blocked outside No3 shower room at base of rain water drain pipe trap due to leaveas compactment. Broken rainwater trap filter at roof gulley.

## No 4 Maintenance
No 4 Tregonwell Almshouse Maintenance Record
Date | Maintenance Action | Company | Labour Cost | Materials Cost | Comments

## Data Table Validation
Not Yet Started
In Progress
Completed
No Action
DO NOT CHANGE THE ABOVE FIELDS: They are used in the worsheets as data references